## Tracker
Supplier 8D / SCAR tracker
Free supplier 8D / SCAR tracker by 8D Gate (8d-gate.vercel.app). Due dates use the Settings sheet (working days, weekends skipped, not public holidays). Your customer's own deadlines always override them.
Rows 5–7: illustrative, fictional examples. Delete them and add your own.
ID | Customer | Part / product | Complaint or SCAR ref | Received | Current step | D3 due | D3 done | D4/D5 due | D4/D5 sent | D8 due | D8 closed | Owner | Next action | Status | Days late
EX-1 | Example Auto GmbH | Bracket 4410 | SCAR-0001 | 2026-09-20 | D5 |  | 2026-09-21 |  |  |  |  | Owner | Replace scrap rate check
EX-2 | Example Foods Ltd | Lid seal 22 | C-0002 | 2026-10-14 | D4 |  | 2026-10-15 |  |  |  |  | Owner | Verify cause on line 2
EX-3 | Example Med Inc | Housing 7 | CAPA-0003 | 2026-09-10 | Closed |  | 2026-09-11 |  | 2026-09-17 |  | 2026-10-08 | Owner | Archive evidence
Formulas:
D3 due = IF([Received]="","",WORKDAY([Received],Settings!$B2))
D4/D5 due = IF([Received]="","",WORKDAY([Received],Settings!$B3))
D8 due = IF([Received]="","",WORKDAY([Received],Settings!$B4))
Status = IF([Received]="","",IF(OR([Current step]="Closed",[D8 closed]<>""),"Closed",IF(AND([D3 done]="",TODAY()>[D3 due]),"OVERDUE D3",IF(AND([D4/D5 sent]="",TODAY()>[D4/D5 due]),"OVERDUE [Complaint or SCAR ref, row above]/[Complaint or SCAR ref]",IF(TODAY()>[D8 due],"OVERDUE D8",IF([D8 due]-TODAY()<=Settings!$B5,"Due soon","On track"))))))
Status = IF([Received]="","",IF(OR([Current step]="Closed",[D8 closed]<>""),"Closed",IF(AND([D3 done]="",TODAY()>[D3 due]),"OVERDUE D3",IF(AND([D4/D5 sent]="",TODAY()>[D4/D5 due]),"OVERDUE D4/[Complaint or SCAR ref, row above]",IF(TODAY()>[D8 due],"OVERDUE D8",IF([D8 due]-TODAY()<=Settings!$B5,"Due soon","On track"))))))
Days late = IF(LEFT([Status],7)<>"OVERDUE","",TODAY()-IF([Status]="OVERDUE D3",[D3 due],IF([Status]="OVERDUE [Complaint or SCAR ref, row above]/[Complaint or SCAR ref]",[D4/D5 due],[D8 due])))
Days late = IF(LEFT([Status],7)<>"OVERDUE","",TODAY()-IF([Status]="OVERDUE D3",[D3 due],IF([Status]="OVERDUE D4/[Complaint or SCAR ref, row above]",[D4/D5 due],[D8 due])))

## Settings
Target | Working days after received (edit to your customer's rules)
D3 containment due | 1
D4/D5 root cause + planned actions due | 5
D8 closed 8D due | 20
'Due soon' warning (calendar days before D8) | 5
Defaults follow the strict 24 h / 5 / 20 working-day rule used by the 8D Gate deadline calculator. They are typical targets, not a standard.
Status: Closed when step is Closed or D8 closed has a date; OVERDUE when a due date passed without the done/sent date; Due soon inside the warning window.